## Task List
| Project Name | Test Project
Project Manager
Date
Version
WORK BREAKDOWN STRUCTURE TEMPLATE - TASKS
Task No. | Task Description | Task Owner | Dependency | Resources Needed | Task Status | Cost | Start Date | Estimated Completion | Finish Date | Notes
1 | Initiation Phase
1.1 | Risk assessment | Jaden M | Meeting | communication tools | Assigned | 3000 | 2020-08-01 | 1 day
1.1.2 | Assets identification | Jaden M
1.1.3 | Weighted Factor Analysis (WFA) | Jaden M |  | PM | Assigned | N/A |  | 1 day
1.1.4 | Risk Identification | Jaden M
1.1.5 | Risk Register | Jaden M | Risk Identification | Dev team | Late | N/A |  | 1 day
2 | Planning Phase
2.1 | Delegate Tasks | Management team
2.1.2 | Breack down the work into steps | Marco.C
2.1.2.1 | Develop a Work Break Structure | Marco.C
2.1.3 | Identify rigth people to assaing macro tasks | Management team |  | Marco.C
2.2 | Define methodology e.g. PMBoK | Marco.C |  | Jaden M
2.2.1 | Define communication method | Management team |  | Corey POWEL
2.2.1.1 | Schedule meeting based on availability |  |  | Dylan MLADINEO
2.2.1.2 | Use Microsoft Meeting/remote commincation |  |  | Management team | Risk Assessment Team
2.2.1.3 | Provide feedback on tasck completition |  |  |  | • Manager of Security Implementation Team
2.2.1.4 | Embrace positive attitudes |  |  |  | • Manager of Security Policy & Compliance Team
2.2.2 | Costs and budget estimation | Marco.C |  |  | • Manager of Project Management Team
2.2.3 | Define Quality standards | Management team
2.2.4 | Research current policy and laws | Manager of Security Policy & Compliance Team
2.2.5 | Research controls | Management team
3 | Execution Phase
3.1 | Ensure a secure data storage processing and transmission
3.1.1 | update e-mail and system encryption
3.1.2 | Implement effective firewall
3.1.3 | device and software update
3.1.4 | Embrace multi-factor authentication
3.1.4.1 | configure Microsoft Office 360
3.2 | define criteria to access to company devices, systems and applications
3.2.1 | Enforce strong password
3.2.2 | Define priviladge on the system
3.2.3 | Limit access to fisical designed areas
4 | Control Phase
4.1 | Access Control
4.1.2 | Review existing controls
4.1.3 | Review existing best practice
4.1.4 | Develop frameworks
4.1.5 | framework implementation
4.1.6 | Develop supportative policy
4.2 | Awareness and Training
4.2.1 | Design and develop security training program
4.2.2 | Training develop
4.3 | Physical and Environmental Protection
4.3.1 | Evaluate areas that needs protection in place
4.3.2 | Security door and CCTV camera installation
4.4 | Contingency plan
5 | Close Phase
5.1 | review new controls
5.1.1 | Testing systems
5.1.2 | Eenforce new policy
5.1.3 | Delegate roles and responsibility

## WBS Tree
WBS TREE Diagram
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## How to Use WBS Template
How to Use WBS Template
The following is a breakdown of the terms and sections in the task list and WBS template.
Task No.: This is a numerical listing of the deliverable, which is further distinguished as you drill down deeper from task to subtask by decimal points to make sure you know exactly where in the process you are.
Task Description: This section details what the deliverable is and also goes into the task and the subtasks necessary to complete it.
Task Owner: Every deliverable, task and subtask needs an owner to make sure the work is getting done, and that person is noted in this column.
Dependency: Some tasks cannot be started until the task before them has been completed, which means it’s dependent on that task and they should be linked. This is the space where you can note task dependencies.
Resources Needed: Whatever the task needs in terms of people, equipment, materials, etc., is listed here.
Task Status: This is where you can track the status of a specific task or subtask. The dropdown menu gives you the option of marking the task as unassigned, assigned, in progress, late or complete.
Cost: Note the financial commitment needed to get the deliverable done.
Start Date: When did work on the deliverable begin? Mark it here.
Estimated Completion: The estimated amount of time allotted for the completion of the deliverable should be noted here.
Finish Date: When the deliverable is done, note the end date here.
Using the Tree Diagram
On the second sheet there is a tree chart to visualize the work breakdown structure, from the highest level at the top to the lowest level at the bottom, where the bottom is more specific and the top more general. You don’t have to add all the extra data you filled into the previous sheet, just the deliverable, task and how every many subtasks are needed to get the work done.